## Sheet1
Weeks
|  |  |  | 2 | 4 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 24 | 26
Task Name | Progress | Start date | End date
Sprint 1
Identify Requirements | 100% | 2024-10-25 | 2024-11-08 | bar: 2
Design UI (wireframes) | 100% | 2025-11-21 | 2025-11-25 | bar: 4
Perform research | 100% | 2025-11-17 | 2025-11-19 | bar: 4 to 8
Setting up development environment & frameworks | 100% | 2025-11-25 | 2025-11-28 | bar: 2
Develop basic question flow | 50% | 2025-11-14 | 2025-12-05 | bar: 2 to 4
Unit Testing | 0% | bar: 2 to 8
Sprint 2
Design architecture diagrams | bar: Weeks 10
Implement Glucocorticoid Routes/pages | bar: Weeks 10 to Weeks 12
Develop and implement sec requirement logic | bar: Weeks 14
Intergration testing | bar: Weeks 10 to Weeks 14
Ethical and legal analysis | bar: Weeks 16
W3C compliance review | bar: Weeks 16
Sprint 3
Hardening | bar: Weeks 18 to Weeks 20
Requirements review against produced software artefact | bar: Weeks 24
Final report write-up | bar: Weeks 18 to Weeks 26
Hand-in | bar: Weeks 26